

1. Overview

Deloitte is one of the best tech corporations that has been serving software solutions for clients. Our services relate to all over the world and has been delivering high and complex software solutions with an ease by the team of experts.

The software domain team is potent, and they are ambitious. And our expertise and services will be more which make our company glance by many clients.

Please, look into our software Development proposal for Daikibo’s telemetry Live Dashboard.

2. Scope

The Characteristics of the project: -

* **Private dashboard with health status of the 9 machines in each of Daikibo's 4 factories, for which they collect telemetry.**
* **Access to the page happens only within client's Intranet.**
* **Authentication is synced to internal authentication server (users can leverage their company-wide accounts).**
* **The dashboard consists of a single page, listing the current statuses of all monitored devices.**
* **The view is collapsible/expandable at a factory level, as well as device level (showing history of statuses).**

You can refer the below image for visual reference and its not the final design, just a mock visual reference.



3. Estimate

|  |  |  |  |
| --- | --- | --- | --- |
| Design | Development | Integration | Total |
| 60 | 180 | 80 | 320 |

\*Man- hours

We will form an international team of 2 software engineers & 1 graphic designer.

* We will be required the help of at least 1 dev-ops engineer from Daikibo’s to hand off the finished product and help us with access to authentication and telemetry databases and services.

4. Timeline

1. [11th of November 2022] **Design starts**
2. [18th of November 2022] **Design is circulated to Daikibo for feedback**
3. [23rd of November 2022] **Design is finalized, and Development starts**
4. [1st of December 2022] **Development is done and version 1 of the product is demonstrated to Daikibo**
5. [9th of December 2022] **Development is finalized, and integration starts**
6. [21st of December 2022] **Integration is completed**

5. Support

This proposals’ main theme is development of the project, and the product is successfully deployed within Daikibo’s infrastructure – we are going to remain available for continuous support. As listed in overview.

You can submit support ticket through our internal support system. The estimate of work described earlier doesn’t cover the continuous support we provide, and any future bug fixes, updates and improvements will be invoiced separately.